## Read me
ERP Cutover Plan Template
Every task, owner and contract seat from data freeze to first invoice. Hours count from the cut, H0, the moment the new system opens for business.
How to use it
1. Set the cut | Open the Runbook sheet and type the date and time of the cut in the shaded cell at the top. Every planned time fills itself in.
2. Move the hours | The offsets in column C are starting points. Replace them with the minutes your last rehearsal really took, then add a buffer.
3. Name the people | Pick partner, employee or contract seat in column G, then type a real name in column I and the signer in column K.
4. Run it | Update Status as the weekend goes. Done, In progress and Blocked change colour. Filter by owner type to give each team its own list.
5. Make the call | The Go or no-go sheet holds the seven criteria, the signatures and the rollback triggers. Fill the shaded thresholds before the call, not during it.
6. Price the seats | The Seats sheet puts KORE1 bill rates beside your own hours so the contract seats are in the budget before the weekend.
Reading the Rollback column
Tail kept | The old system is still the system of record. Rolling back means reopening it and lifting the freeze.
Clipped | Live work sits in the new system. Rolling back means restoring the old one from backup and replaying every entry since the cut.
One way | Something has left the building. Rolling back can’t recall it. You credit, reverse or correct.
Owners
Employee | Your own staff.
Partner | Your implementation partner.
Contract seat | A contractor you bring on for the window.
Good to know
Hours | H-96 is 96 hours before the cut. H+48 is 48 hours after it.
Rates | Reference rates are the 25th percentile, median and 75th percentile of KORE1 bill rates in each cell of the KORE1 Contract Rate Index 2026-Q4, effective October 16, 2026. Cells come from KORE1 W2 contract placements started 2023 to 2026, with five or more in each.
Not advice | Hours are starting points, not KORE1 terms. Move them to match your rehearsal timings. This is a template, not legal, audit or validation advice. Have your controller and your auditor review it before the cut, and on a validated system your quality lead too.
Source | Written by Colin Boothe in partnership with KORE1. Version October 2026. kore1.com/erp-cutover-plan-template/

## Runbook
ERP Cutover Plan, Freeze to First Invoice
KORE1 and Colin Boothe. Shaded cells are yours to fill. Hours count from the cut (H0).
The cut (H0), date and time
Cutover lead
Executive sponsor
Rollback caller and backup
Hypercare starts
ID | Phase | Hour offset | Planned time | Task | What it covers | Owner type | Owner role | Named owner | Signs off | Signer name | Rollback after it | If you roll back after it | Status | Actual start | Actual finish | Notes
A1 | Freeze | -96 |  | Start the master data freeze | No new customers, vendors or items in the old system without the controller’s initials. | Employee | Controller |  | Controller |  | Tail kept | Lift the freeze. Nothing downstream has moved. | Not started
A2 | Freeze | -96 |  | Freeze configuration and integrations | From here every change in the new system goes through the change log, even the ones that look harmless. | Partner | Implementation lead |  | Partner lead and IT lead |  | Tail kept | Lift the freeze. Parked changes wait their turn. | Not started
A3 | Freeze | -84 |  | Back up both systems and test a restore | A backup you haven’t restored is a hope. Prove the way back before you need it. | Contract seat | ERP consultant |  | IT lead |  | Tail kept | Keep both backups. Every later rollback leans on them. | Not started
A4 | Freeze | -72 |  | Reset the plan from your last rehearsal | Swap every guess for the minutes the last mock cutover really took, then add a buffer. | Contract seat | Project manager |  | Partner lead |  | Tail kept | Revert the plan file. No system was touched. | Not started
A5 | Freeze | -60 |  | Check production access for named users | Roles, single sign-on, multi-factor and approval routing, tested with real accounts for day one. | Contract seat | Help desk |  | IT lead |  | Tail kept | Reset the roles. Minutes, not hours. | Not started
B1 | Final loads and reconciliations | -48 |  | Put the old system in read-only | Last postings go in, period cutoffs are taken, and nobody types into the old system after this. | Employee | IT administrator |  | Controller |  | Tail kept | Switch it back to read and write. | Not started
B2 | Final loads and reconciliations | -44 |  | Extract the final data from the old system | Masters first, then open items, then balances, each with a row count and a control total. | Contract seat | Data analyst |  | Partner data lead |  | Tail kept | Delete the extract and run it again. | Not started
B3 | Final loads and reconciliations | -36 |  | Load the masters and check the counts | Customers, vendors, items, price lists and the chart of accounts map. Counts and totals must match. | Contract seat | Data analyst |  | Partner data lead |  | Tail kept | Purge by load ID and reload. | Not started
B4 | Final loads and reconciliations | -30 |  | Load the open transactions | Open receivables and payables, open orders and purchase orders, and stock by location and lot. | Contract seat | ERP consultant |  | Controller and operations lead |  | Tail kept | Purge by load ID before anything posts. | Not started
B5 | Final loads and reconciliations | -24 |  | Post the opening balances | The trial balance goes into the new ledger as one journal, with the old system’s totals beside it. | Employee | General ledger accountant |  | Controller |  | Tail kept | Reverse by journal, or wipe and reload while the old system is still live. | Not started
B6 | Final loads and reconciliations | -20 |  | Reconcile the money | Trial balance, receivables, payables and inventory value, each tied to the old system with every variance named. | Contract seat | Data analyst |  | Controller |  | Tail kept | A failed tie-out is a no-go, not a rollback. | Not started
B7 | Final loads and reconciliations | -16 |  | Reconcile the operations | Stock counts by location, open order and purchase order counts, and a spot check of price lists. | Employee | Operations lead |  | Partner lead |  | Tail kept | A failed count is a no-go. Recount before the call. | Not started
B8 | Final loads and reconciliations | -12 |  | Point the integrations at production, held | EDI, ecommerce, payments, bank feeds and payroll, each tested with one real message that waits for release. | Partner | Integration lead |  | IT lead |  | Tail kept | Repoint to test. Held messages stay held. | Not started
B9 | Final loads and reconciliations | -10 |  | Triage every open defect | Each gets a severity, a workaround and an owner. Nothing goes into the call as a mystery. | Contract seat | Project manager |  | Partner lead |  | Tail kept | Defect log only. Nothing to undo. | Not started
C1 | Go or no-go and the cut | -4 |  | Hold the go or no-go call | Seven criteria, read out loud. Any one that fails makes it a no-go. | Employee | Executive sponsor |  | Controller, operations lead and partner lead |  | Tail kept | A no-go costs a rescheduled weekend. Needs A3 and B1. | Not started
C2 | Go or no-go and the cut | -2 |  | Name the rollback caller and the trigger | Write down who can call it, who backs them up and the numbers that make the call for them. | Partner | Implementation lead |  | Executive sponsor |  | Tail kept | Last clean rollback. Reopen the old system and lift the freeze. | Not started
C3 | Go or no-go and the cut | -1 |  | Lock the old system and release the integrations | The old system stays readable for lookups. Held messages start to flow. | Employee | IT administrator |  | Executive sponsor |  | Clipped | Past here, rollback means restoring from A3 and replaying every entry. | Not started
C4 | Go or no-go and the cut | 0 |  | Open the new system to users | Single sign-on on, announcement out, command center live. This is H0, the cut. | Partner | Implementation lead |  | Executive sponsor |  | Clipped | Restore from A3 and replay everything entered since H0. | Not started
D1 | First transactions | 1 |  | Run the five smoke transactions | A sales order to an invoice draft, a purchase order to a bill, a payment, a journal and a stock transfer. | Employee | Power users |  | Process owners |  | Clipped | Restore from A3, then replay these and what followed. | Not started
D2 | First transactions | 2 |  | Release the held messages and watch the queues | Check the error queues every thirty minutes. Replay failures from the source systems. | Contract seat | ERP consultant |  | IT lead |  | Clipped | Replay from the source systems. Needs C3. | Not started
D3 | First transactions | 4 |  | Stand up the floor | The command center takes tickets, and a floor walker sits in each department. | Contract seat | Help desk |  | Partner lead |  | Clipped | Staffing only. The rollback is the data, not the desk. | Not started
D4 | First transactions | 8 |  | Reconcile day one | New transactions against their source documents, stock movements and cash, signed before anyone sleeps. | Contract seat | Data analyst |  | Controller |  | Clipped | Correct by journal. A full rollback needs A3 and a replay. | Not started
D5 | First transactions | 24 |  | Hold the day-one review | Defects, workarounds, blocked users and the stop-loss rule, read out and decided. | Employee | Executive sponsor |  | Partner lead and controller |  | Clipped | The last easy rollback call. Restore from A3 and replay. | Not started
E1 | First invoice and hand-off | 36 |  | Run the first billing batch | Draft invoices checked line by line against orders before one is released. | Employee | Billing lead |  | Controller |  | Clipped | Delete the drafts. Nothing has left the building. | Not started
E2 | First invoice and hand-off | 48 |  | Send the first customer invoice | Tax, terms and remit-to all checked. This is the first thing a customer sees. | Employee | Billing lead |  | Controller |  | One way | A sent invoice can only be credited, never recalled. | Not started
E3 | First invoice and hand-off | 96 |  | Close the runbook and hand off | Open items go to the hypercare list with a name and a date, and the support roster is confirmed. | Partner | Implementation lead |  | Executive sponsor |  | One way | Hand-off record. Open items now live on the hypercare list. | Not started

## Go or no-go
Go or no-go, and rollback
Go only if all seven are true. Any one that fails makes it a no-go. A no-go is the plan working.
# | Go criterion | Your threshold | Status | Checked by | Time
1 | Every final load ties to the old system within [$ tolerance], and each variance has a name next to it. |  | Open
2 | The last rehearsal finished inside the window, with at least [8] hours to spare. |  | Open
3 | No severity 1 defect is open, and each severity 2 has a workaround someone has tried. |  | Open
4 | Each integration passed one real test message in production, held and not released. |  | Open
5 | A sample of [10] users per department signed in with the right role. |  | Open
6 | The roster has a backup for every seat, contract seats included, and everyone has the bridge number. |  | Open
7 | Rollback was rehearsed and timed, and the caller has a name. |  | Open
Result
| Signature before H-4 | Name | Signed | Time
| Executive sponsor |  | No
| Controller |  | No
| Operations lead |  | No
| Partner cutover lead |  | No
| Quality lead (validated systems only) |  | No
# | Rollback trigger after the cut | Your threshold | Called by | Backup
1 | More than [25] integration messages fail in [2] hours and can’t be replayed.
2 | The ledger won’t tie to receivables, payables or stock after [2] correction passes.
3 | Warehouse or finance can’t ship or invoice by [H+8].
4 | A load error turns up in masters that live transactions already use.
After the cut, rolling back means restoring from the A3 backup and replaying every entry made since H0. Pick the numbers and the caller before the call.

## Seats
Contract seats for the cutover window
KORE1 Contract Rate Index 2026-Q4, effective October 16, 2026. Bill rates per hour. Hours are an assumption. Change them.
Seat | KORE1 cell | n | Low | Median | High | Tasks in the runbook | Hours | Cost at median | Your quoted rate | Cost at your rate
ERP consultant | ERP / NetSuite / Salesforce consultant, Multi-state | 15 | 73 | 91 | 123 | A3, B4, D2 | 60
Data analyst | Data analyst / BI developer, Primarily Southern California | 11 | 69 | 115 | 116 | B2, B3, B6, D4 | 60
Help desk | Help desk / IT support technician, Primarily Southern California | 39 | 41 | 49 | 55 | A5, D3 | 60
Project manager | IT project / program manager, Primarily Southern California | 21 | 105 | 116 | 124 | A4, B9 | 60
Total
Weekend and overnight hours can trigger overtime for W2 contractors. Check the U.S. Department of Labor rules and your state before you set the hours.
A seat quote for your req: kore1.com/bill-rate-quote/